## Sheet1
AVV (Autonomous Vision-aided Vehicle)
TASK NAME | ASSIGNED TO | START DATE | DUE DATE | DURATION | % DONE | SPRINT/MILESTONE | PRIORITY | SPRINT/MILESTONE
RFP Write-up | M. Ali and Yousaf | 2019-01-07 | 2019-01-09 | 2 | 100 | Phase 1 |  | Phase 1
Proposal Write-up | M. Ali and Yousaf | 2019-01-15 | 2019-01-17 | 2 | 100 | Phase 1 |  | Phase 1
Oral Presentation | M. Ali and Yousaf | 2019-01-22 | 2019-01-24 | 2 | 100 | Phase 1 |  | Phase 1
Initialize Inventory | M. Ali and Yousaf | 2019-01-25 | 2019-01-30 | 5 | 70 | Phase 1 |  | Phase 1
Structural Design | Yousaf | 2019-01-26 | 2019-02-01 | 6 | 80 | Phase 1 |  | Phase 1
Initial Vision System Set-up | M. Ali | 2019-01-25 | 2019-02-06 | 12 | 0 | Phase 1 |  | Phase 1
Casting Main Body | Yousaf | 2019-02-04 | 2019-02-08 | 4 | N/A | Phase 1 |  | Phase 1
First Progress Report | M. Ali and Yousaf | 2019-02-04 | 2019-02-07 | 3 | 100 | Phase 2 |  | Phase 2
Vision System Testing | M. Ali and Yousaf | 2019-02-07 | 2019-02-18 | 11 | 0 | Phase 2 |  | Phase 2
Main Body and Drive System Integration | M. Ali and Yousaf | 2019-02-19 | 2019-02-20 | 1 | 0 | Phase 2 |  | Phase 2
Drive System Testing | M. Ali and Yousaf | 2019-02-09 | 2019-02-18 | 9 | 0 | Phase 2 |  | Phase 2
Sensor Testing | M. Ali and Yousaf | 2019-02-19 | 2019-02-25 | 6 | 0 | Phase 2 |  | Phase 2
Sensor and Vision System Integration | M. Ali and Yousaf | 2019-02-26 | 2019-03-12 | 14 | 0 | Phase 2 |  | Phase 2
Update Progress Report | M. Ali and Yousaf | 2019-03-12 | 2019-03-15 | 3 | 0 | Phase 3 |  | Phase 3
Complete Testing Stage | M. Ali and Yousaf | 2019-03-16 | 2019-04-10 | 25 | 0 | Phase 3 |  | Phase 3
Final Project Report, Poster Presentation and Documentation | M. Ali and Yousaf | 2019-04-11 | 2019-04-25 | 14 | 0 | Phase 4 |  | Phase 4